North Silverdale Commercial, Industrial & Residential Lands Planning Proposal – Project Timeline

|  |  |  |
| --- | --- | --- |
| **Principal Steps** | **Anticipated commencement** | **Anticipated completion** |
| Commencement(Gateway Determination) | April 2013 | April 2013 |
| Government agency consultation (pre-exhibition) | May 2013 | June 2013 |
| Required studies | June 2013 | December 2013 |
| Public exhibition | January 2014 | February 2014 |
| Government agency consultation (during and post-exhibition) | January 2014 | March 2014 |
| Consideration of Submissions | March 2014 | April 2014 |
| Consideration of Proposal Post Exhibition | May 2014 | June 2014 |
| RPA resolve to request the making of the Plan | July 2014 | September 2014 |