|  |  qA284378 14/03500 Department Generated Correspondence (Y) |
| --- | --- |

Planning AND INFRASTRUCTURE

______________Growth Planning and Delivery___________

gateway determination EXTENSIONS FOR FAIRFIELD COUNCIL

Purpose

To recommend that the Director, Metropolitan Delivery (Parramatta), as the Minister’s delegate, alter the Gateway Determination for:

  - PP_2011_FAIRF_004_00 (Amdt 2)

  - PP_2012_FAIRF_003_00 (Amdt 6)

Recommendation

- It is RECOMMENDED that the Minister’s delegate:

agree pursuant to s56(7) of the Environmental Planning and Assessment Act 1979, to amend the Gateway Determination to extend the time to complete the following planning proposals by the time listed below, and;

sign the letter to Fairfield Council (Tag A).

| Planning Proposal | Proposed Extension | Proposed New Due Date |
| --- | --- | --- |
| PP_2011_FAIRF_004_00 13-21 Rossetti St, Wetherill Park | 3 months | 13 May 2014 (was 13 February 2014) |
| PP_2012_FAIRF_003_00 Additional uses at 96 Newton Rd, Wetherill Park | 3 months | 12 June 2014 (was 12 March 2014) |

Current position

PP_2011_FAIRF_004_00 – Amendment No. 2 - Rezoning of 13-21 Rossetti St, Wetherill Park

Current due date: 13 February 2014

Current status: The proposal was sent to Legal requesting PC Opinion on 28 August 2013. The maps are currently undergoing a fifth map check.

Background: The proposal seeks to rezone the site from R2 to B2

Reason for extension: Delays due to map checks.

PP_2012_FAIRF_003_00 – Amendment No. 6 – Additional Permitted Uses at 96 Newton Rd and 449 Victoria St, Wetherill Park

Current due date: 12 March 2014

Current status: The proposal was sent to Legal requesting PC Opinion on 20 November 2013. Awaiting map checks.

Background: The proposal seeks to permit additional permitted uses ‘hotel or motel accommodation’ and ‘medical centre’ on the site.

Reason for extension: Delays due to map checks.

Prepared by: Georgina Ballantine

Planning Officer

Metropolitan Delivery (Parramatta)

Phone: 02 9860 1568

Endorsed:

25/2/2014

Rachel Cumming

Director

Metropolitan Delivery (Parramatta)

Delegate of the Minister for Planning and Infrastructure