**PROJECT TIMELINE – LOWER LEWIS PONDS SA3 PLANNING PROPOSAL**

|  |  |  |  |
| --- | --- | --- | --- |
| No | Task | Commencement | Completion |
| 1 | Gateway DeterminationObtain Gateway Determination | September 2014 | September 2014 |
| 2 | Public ExhibitionAgency and community consultation to be undertaken as part of the formal pubic exhibition of the planning proposal in accordance with any conditions of the Gateway Determination | October 2014 | November 2014 |
| 3 | Consider submissions and document finalizationFollowing the public exhibition council staff are to consider, respond and report to council on any submissions received and issues raised, and make any relevant changes to the planning proposal.This process will determine amongst other things the following:* Whether or not to endorse and/or support the planning proposal
* Whether or not to endorse the planning proposal (as (exhibited): or
* Whether or not to endorse the planning proposal (as amended)
 | November 2014 | December 2014 |
| 4 | Submission to the Department and/or Parliamentary Counsel Council to forward the planning proposal to the department and / or Parliamentary Counsel following public exhibition (including and changes made) | December 2014 | December 2014 |
| 5 | NotificationNotification of LEP amendment being made | January 2015 | January 2015 |