**STRATHFIELD GOLF CLUB – PLANNING PROPOSAL PROJECT TIMELINE**

|  |  |
| --- | --- |
| **Stage** | **Completion date** |
| Gateway determination (anticipated) | 21 October 2013 |
| Completion of required studies | 16 December 2013 |
| Government agency consultation | 28 January 2014 |
| Public exhibition period | 28 January – 25 February 2014 |
| Consideration of submissions | 17 March 2014 |
| Consideration of a proposal post exhibition | 1 April 2014 |
| Report to Council results of public exhibition | 15 April 2014 |
| RPA decision to make the plan (if delegated) | 26 May 2014 |
| Forwarding of LEP amendment to DPI for notification (if delegated) | 23 June 2014 |