# Part 6 Project timeframe

The following table outlines Council’s anticipated timetable for the completion of the Planning Proposal. Council anticipates that the process will take approximately 2.5 years from the date of the Gateway Determination.

Council suggests that the preparation of a Local Environmental Study will be required to address the issues identified and has allowed 18 months for the preparation of the requisite information to support the rezoning. It is proposed that consultation with Government Departments should occur prior to the public exhibition process to minimise the post exhibition amendments to the plan.

|  |  |  |
| --- | --- | --- |
| **Step** | **Criteria** | **Project timeline** |
| 1 | Anticipated commencement date (date of Gateway determination) | July 2016 |
| 2 | Anticipated timeframe for the completion of required technical information | January 2018 |
| 3 | Timeframe for government agency consultation (pre and post exhibition as required by Gateway determination) | March 2018 |
| 4 | Commencement and completion dates for public exhibition period | May 2018 |
| 5 | Dates for public hearing (if required) | Not anticipated |
| 6 | Timeframe for consideration of submissions | July 2018 |
| 7 | Timeframe for the consideration of a proposal post exhibition | September 2018 |
| 8 | Date of submission to the department to finalise the LEP | October 2018 |
| 9 | Anticipated date RPA will make the plan (if delegated) | December 2018 |
| 10 | Anticipated date RPA will forward to the department for notification. | December 2018 |