|  |  |
| --- | --- |
| **Planning proposal stage** | **Timeframe** |
| Anticipated commencement date (date of Gateway determination) | Dependant on Department.  Week 0 |
| Completion of required technical information | End week 8 |
| Advisory report to Council | Previously completed - 25 July 17  Will use Council delegation as Relevant Planning Authority |
| Commencement and completion dates for public exhibition period | Week 12- Week 16 |
| Government agency consultation | End Week 19 |
| Consideration of submissions | End Week 19 |
| Post exhibition report to Council | End Week 24 |
| Submission of planning proposal to DP&E to finalise the LEP |  |
| Council decision to make the LEP amendment (if delegated) | End week 24 |
| Forwarding of LEP amendment to DP&E for notification (if delegated) | End week 30 |