**Timeline - Planning Proposal –Lot 6 DP 3944 No. 39 Dell Road West Gosford**

**Rezoning to Part IN1 – General Industrial and Part E2 – Environmental Conservation**.

.• anticipated commencement date (date

of Gateway determination) - February 2016

• anticipated timeframe for the

completion of required technical information - May 2016

• timeframe for government agency

consultation (pre and post exhibition as

required by Gateway determination) - July 2016

• commencement and completion dates

for public exhibition period - August 2016

• dates for public hearing (if required) - N/A

• timeframe for consideration of

submissions - September 2016

• timeframe for the consideration of a

proposal post exhibition - N/A

• date of submission to the department to

finalise the LEP - November 2016

• anticipated date RPA will make the plan

(if delegated) - December 2016

• anticipated date RPA will forward to the

department for notification. - December 2016