|  |  |
| --- | --- |
| **Plan Making Step** | **Estimated Completion**  |
| Submission of Planning Proposal to Council. | Received 25 March 2014.  |
| Requested amendments to Planning Proposal received by Council including amended Traffic and Parking Report and a Site Contamination Remediation Methodology. | Received 24 April 2014. |
| Report and Recommendation on Planning Proposal considered by Council at its Planning and Strategy Committee Meeting. | Reported 5 May 2014. |
| Submission of Planning Proposal to Department of Planning and Environment for consideration of Gateway Determination. | Sent 13 May 2014. |
| Council request that Sydney Water both amend the Planning Proposal (in relation to the proposed zoning for part of the site) and prepare a Voluntary Planning Agreement.  At this time Council also requested that Sydney Water consider increasing the amount of the land that is to be dedicated. | Sent 13 May 2014. |
| Gateway Determination. | Issued 30 June 2014.  |
| Completion of draft Voluntary Planning Agreement to accompany Planning Proposal. | Finalised on 5 November 2014 incorporating further amendments and additional considerations requested by Council. |
| Completion of Zoning Amendments to Planning Proposal. | Agreement from Sydney Water for amendment received 7 November 2014. Revised Planning Proposal submitted to Department on 20 November 2014. Department’s revised Determination dated 19 December 2014.  |
| Draft Voluntary Planning Agreement and amended Planning Proposal considered by Council. | Council Resolution 5 May 2014 enabled exhibition of a Draft Voluntary Planning Agreement and amended Planning Proposal. Step Completed. |
| Public exhibition period (over 28 days in accordance with Council’s Policy to extend notifications over December and January). | 10 January 2015 to 9 February 2015, following receipt of revised Gateway Determination on 19 December 2014.  |
| Timeframe for government agency consultation.  | As per Public exhibition period and in accordance with Gateway Determination. |
| Council consideration of Public Exhibition submissions.   | Council Meeting March 2015. |
| Date of submission to the Department to finalise the LEP. | April 2015.  |
| Anticipated date RPA (Manly Council) will make the plan (if delegated). | Pending DoPI advice. |
| Anticipated date RPA (Manly Council) will forward to the Department for notification. | Pending DoPI advice. |

**Amended Project Time Line – Amending MLEP 4 - Sydney Water Fairlight Reservoir**

**MC/14/137522**