**Timeline - Planning Proposal - Amendments to Home Business Estate LEP - Kings Ave Terrigal.**

• anticipated commencement date (date

of Gateway determination) - mid August 2014

• anticipated timeframe for the

completion of required technical information - N/A

• timeframe for government agency

consultation (pre and post exhibition as

required by Gateway determination) - N/A

• commencement and completion dates

for public exhibition period - mid September/October 2014

• dates for public hearing (if required) - N/A

• timeframe for consideration of

submissions - end October 2014

• timeframe for the consideration of a

proposal post exhibition - November 2014

• date of submission to the department to

finalise the LEP - December 2014

• anticipated date RPA will make the plan

(if delegated) - end January 2014

• anticipated date RPA will forward to the

department for notification. - end January 2014