Part 6 – Project Timeline

**Table 3.** Estimated timeline for preparing amending Local Environmental Plan

| Milestone | Timeline |
| --- | --- |
| Start | Finish |
| Council Resolution | June 2022 | 22 July 2022 |
| Gateway determination | July 2022 | Aug 2022 |
| Anticipated timeframe for the completion of required technical information | NA |  |
| Government agency consultation | Aug 2022 | Oct 2022 |
| Public exhibition period | Oct 2022 | Nov 2022 |
| Notice of Public Hearing | NA |  |
| Public Hearing\* | NA |  |
| Consideration of submissions | Nov 2022 | Dec 2022 |
| Report to Council post Exhibition | Jan 2023 | Feb 2023 |
| Date of submission to the Department to finalise the LEP | NA |  |
| Timeframe for drafting of LEP & Map Checks | Feb 2023 | Apr 2023 |
| Anticipated date RPA will make the plan (under delegation) | Apr 2023 | May 2023 |
| Anticipated date RPA will forward to the department for notification. | May 2023 | June 2023 |